## general_report
JIRA
Displaying 26 issues at 22/Feb/17 9:04 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Account | Actual End | Actual Start | Adminitrack ID | Baseline Effort | Baseline End | Baseline Start | Baseline end date | Baseline start date | Date of Baselining | Dev Priority | End date | Epic Color | Epic Link | Epic Name | Epic Status | Epic/Theme | External issue ID | Flagged | Found By | Found Date | Gantt Options | Gantt-Chart | Iteration | Latest End | Latest Start | MS-Project ID | POC | POC Priority | Planned End | Planned Start | Progress | QA Date | Rank | Ranking | Reopened By | Reopened Date | Resolution Description | Resolved By | Severity | Sprint | Start date | Steps to Reproduce | Team | Velocity % | [CHART] Date of First Response
Project 1 | PFA-26 | Create a process that can run a period of time Month/Season/Year and generate a report | Task | Open | 2 | Unresolved | Dev 2 | Dev 1 | Dev 1 | 2017-02-01 10:29 | 2017-02-22 08:50 | 2017-02-22 08:50 |  |  |  | Power Flow |  | 0 | 1 |  | 432000 | 432000 |  | 0% |  |  |  | Generate a web page report |  | 0% | 0% |  | 432000 | 432000 |  | None | [10 empty] | 2017-02-21 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-04-17 10:30 | 2017-03-27 10:30 |  |  | 0¦i01yo7: | [7 empty] | 2017-02-01 |  | None
Project 2 | DS-34 | Extract Bus Loads from MSIO SE Files, store in the Database. | Task | Open | 2 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2017-02-01 10:55 | 2017-02-22 09:00 | 2017-02-22 09:00 |  |  |  | Load |  | 0 | 1 |  | 57600 | 57600 |  | 0% | [5 empty] | 0% | 0% |  | 57600 | 57600 |  | None | [22 empty] | None |  |  |  | Gerry Binder |  | 2017-03-28 11:00 | 2017-03-24 11:00 |  |  | 0¦i01yof: | [9 empty] | None
Project 1 | PFA-14 | Create a Process that loads Historical Outages and Constraints, Performs a Power Flow Calculation, and determine what outages may have the largest impact on any given constraint Determine Possible Node Impact with Shift Factors | New Feature | Open | 2 | Unresolved | Dev 2 | Dev 1 | Dev 1 | 2017-01-27 11:42 | 2017-02-22 08:50 | 2017-02-22 08:50 |  |  |  | Outage/Outage Factors |  | 0 | 1 |  | 144000 | 144000 |  | 0% | [5 empty] | 0% | 0% |  | 144000 | 144000 |  | None | [10 empty] | 2017-02-02 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-03-24 12:00 | 2017-03-20 11:40 |  |  | 0¦i01ylb: | [7 empty] | 2017-01-27 |  | None
Project 1 | PFA-8 | Add Right Clicks for Line/Outage show in NI Panel | New Feature | Open | 1 | Unresolved | Dev 1 | Dev 1 | Dev 1 | 2017-01-03 11:29 | 2017-02-22 08:25 | 2017-02-22 08:25 |  |  |  | Outage/Outage Factors |  | 0 | 1 |  | 57600 | 57600 |  | 0% | [5 empty] | 0% | 0% |  | 57600 | 57600 |  | None | [10 empty] | 2017-01-04 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-03-22 11:00 | 2017-03-20 10:39 |  |  | 0¦i01v0v: | [7 empty] | 2017-01-03 |  | None
Project 2 | DS-42 | Store ERCOT Line and Transformer rating in the DB | Improvement | Open | 2 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2017-02-02 10:19 | 2017-02-22 08:59 | 2017-02-22 08:59 |  |  |  | Constraints |  | 0 | 1 |  | 86400 | 86400 |  | 0% | [5 empty] | 0% | 0% |  | 86400 | 86400 |  | None | [22 empty] | None |  |  |  | Rick Zabrosky |  | 2017-03-23 10:30 | 2017-03-20 10:30 |  |  | 0¦i01yqf: | [9 empty] | None
Project 3 | COOLAPP-1782 | FTR Details tool, Add a row at bottom diplaying all column totals | New Feature | Open | 2 | Unresolved | Dev 4 | Dev 1 | Dev 1 | 2017-01-27 11:54 | 2017-02-22 08:47 | 2017-02-22 08:47 |  |  |  | FTRs |  | 0 | 1 |  | 115200 | 115200 |  | 0% | [5 empty] | 0% | 0% |  | 115200 | 115200 |  | None | [21 empty] | n.a. | None |  |  |  | Matt Tunno |  | 2017-03-22 12:00 | 2017-03-16 12:00 |  |  | 0¦i01ylz: | [9 empty] | None
Project 2 | DS-52 | Create application and method to take ercot psse daily files and import them into tranzer | Improvement | Open | 2 | Unresolved | Dev 5 | Dev 1 | Dev 1 | 2017-02-10 10:55 | 2017-02-22 08:38 | 2017-02-22 08:38 | [5 empty] | 0 | 1 |  | 288000 | 288000 |  | 0% |  |  |  | Requires use of mapping task and a method to adjust the tranzer topology to match the line configuration of the psse files as well as the ratings of the lines. Also all associated contingencies on tranzer will need modified by this information |  | 0% | 0% |  | 288000 | 288000 |  | None | [22 empty] | None |  |  |  | Rick Zabrosky |  | 2017-03-29 11:00 | 2017-03-15 11:00 |  |  | 0¦i01ytj: | [9 empty] | None
Project 3 | COOLAPP-1758 | ERCOT LiveScreen and Snapshots do not display published shadow price information | Enhancement | Open | 2 | Unresolved | Dev 4 | Dev 1 | Dev 1 | 2016-11-30 16:09 | 2017-02-22 08:46 | 2017-02-22 08:46 |  |  |  | Live Screens |  | 0 | 1 |  | 28800 | 28800 |  | 0% | [5 empty] | 0% | 0% |  | 28800 | 28800 |  | None | [21 empty] | n.a. | None |  |  |  | James Macintosh |  | 2017-03-15 16:00 | 2017-03-14 16:00 |  |  | 0¦i01vb3: | [9 empty] | None
Project 1 | PFA-16 | Adjust Load By breakdown to the Actual Load for Historical and forecasted load for future. First step use the distribution factor currently in the NI file. | New Feature | Open | 1 | Unresolved | Dev 1 | Dev 1 | Dev 1 | 2017-01-27 11:44 | 2017-02-22 08:25 | 2017-02-22 08:25 |  |  |  | Load |  | 0 | 1 |  | 115200 | 115200 |  | 0% | [5 empty] | 0% | 0% |  | 115200 | 115200 |  | None | [10 empty] | 2017-02-01 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-03-20 12:00 | 2017-03-14 12:00 |  |  | 0¦i01ylr: | [7 empty] | 2017-01-27 |  | None
Project 2 | DS-31 | Use Load for SE file to compare to Dayzer Run Data for the Date Time. | Improvement | Open | 1 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2016-12-20 14:21 | 2017-02-22 08:58 | 2017-02-22 08:58 |  |  |  | Load |  | 0 | 1 |  | 86400 | 86400 |  | 0% | [5 empty] | 0% | 0% |  | 86400 | 86400 |  | None | [22 empty] | None |  |  |  | Gerry Binder |  | 2017-03-17 11:30 | 2017-03-14 11:30 |  |  | 0¦i01uzj: | [9 empty] | None
Project 2 | DS-45 | Compare MISO/SPP SE files with Tranzer Output comparing Generation Differences | Enhancement | Open | 2 | Unresolved | Dev 1 | Dev 1 | Dev 1 | 2017-02-02 11:21 | 2017-02-22 08:24 | 2017-02-22 08:24 |  |  |  | Power Flow |  | 0 | 1 |  | 57600 | 57600 |  | 0% | [5 empty] | 0% | 0% |  | 57600 | 57600 |  | None | [22 empty] | None |  |  |  | Gerry Binder |  | 2017-03-13 11:30 | 2017-03-09 11:30 |  |  | 0¦i01yrb: | [9 empty] | None
Project 3 | COOLAPP-1760 | Enable "like month" functionality in FTR Details screens | Enhancement | Open | 2 | Unresolved | Dev 4 | Dev 1 | Dev 1 | 2016-11-30 16:11 | 2017-02-22 08:43 | 2017-02-22 08:43 |  |  |  | FTRs |  | 0 | 1 |  | 144000 | 144000 |  | 0% |  |  |  | Enable "like month" functionality in FTR Details screens, similar to what we have for inc/dec details. This would be a significant timesaver for everyone who trades CRRs, and for annual auctions can add up to 20-30min of time wasted by each trader for each auction, amounting to significant workhours over the course of a year. May be best to introduce in a duplicate or new standalone tool to avoid any further issues with current FTR Details functionality. |  | 0% | 0% |  | 144000 | 144000 |  | None | [21 empty] | n.a. | None |  |  |  | James Macintosh |  | 2017-03-14 16:00 | 2017-03-07 16:00 |  |  | 0¦i01van: | [9 empty] | None
Project 2 | DS-37 | Store MISO Line Ratings and Transformer Ratings. | Improvement | Open | 3 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2017-02-02 09:48 | 2017-02-22 08:57 | 2017-02-22 08:57 |  |  |  | Constraints |  | 0 | 1 |  | 115200 | 115200 |  | 0% |  |  |  | Store the Line key from the comments and the ratings. |  | 0% | 0% |  | 115200 | 115200 |  | None | [22 empty] | None |  |  |  | Gerry Binder |  | 2017-03-13 10:00 | 2017-03-07 10:00 |  |  | 0¦i01ypb: | [9 empty] | None
Project 1 | PFA-42 | NI Code, Expose quick methods to highlight a line or branch. | New Feature | Open | 2 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2017-02-14 11:23 | 2017-02-22 08:56 | 2017-02-22 08:56 |  |  |  | Constraints, Load, Outage/Outage Factors |  | 0 | 1 |  | 57600 | 57600 |  | 0% | [5 empty] | 0% | 0% |  | 57600 | 57600 |  | None | [10 empty] | 2017-02-15 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-03-06 11:30 | 2017-03-02 11:30 |  |  | 0¦i01yun: | [7 empty] | 2017-02-14 |  | None
Project 2 | DS-53 | Strip Logic to Merge PJM/MISO raw files. | Enhancement | Open | 1 | Unresolved | Dev 1 | Dev 1 | Dev 1 | 2017-02-14 10:49 | 2017-02-22 08:24 | 2017-02-22 08:24 |  |  |  | Power Flow |  | 0 | 1 |  | 115200 | 115200 |  | 0% | [5 empty] | 0% | 0% |  | 115200 | 115200 |  | None | [22 empty] | None |  |  |  | Jeff Erdely |  | 2017-03-08 11:00 | 2017-03-02 11:00 |  |  | 0¦i01yu7: | [9 empty] | None
Project 1 | PFA-10 | Show Unmapped Outage and link to Hand Mapping tool for Trader to Map | New Feature | Open | 1 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2017-01-03 11:31 | 2017-02-22 08:54 | 2017-02-22 08:54 |  |  |  | Outage/Outage Factors |  | 0 | 1 |  | 28800 | 28800 |  | 0% | [5 empty] | 0% | 0% |  | 28800 | 28800 |  | None | [10 empty] | 2017-01-09 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-03-01 12:00 | 2017-03-01 11:46 |  |  | 0¦i01v1b: | [7 empty] | 2017-01-03 |  | None
Project 1 | PFA-25 | Create a job that runs Power Flow/ Shift Factor Calculations developed for all outages for tomorrow and generate a report for the Traders | Task | Open | 2 | Unresolved | Dev 2 | Dev 1 | Dev 1 | 2017-02-01 10:24 | 2017-02-22 08:49 | 2017-02-22 08:49 |  |  |  | Shift Factors |  | 0 | 1 |  | 432000 | 432000 |  | 0% |  |  |  | Possible Web page output with right clicks to open nodes in Details tool. |  | 0% | 0% |  | 432000 | 432000 |  | None | [10 empty] | 2017-02-21 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-03-20 10:30 | 2017-02-27 10:30 |  |  | 0¦i01ynz: | [7 empty] | 2017-02-01 |  | None
Project 1 | PFA-28 | Capture Caiso Nodal Group Constraints | Enhancement | Open | 2 | Unresolved | Dev 4 | Tyler Charles | Dev 1 | 2015-01-27 13:55 | 2017-02-22 08:40 | 2017-02-22 08:40 |  |  |  | Constraints |  | 0 | 1 |  | 144000 | 144000 |  | 0% |  |  |  | Add a new screen in CA to view, |  | 0% | 0% |  | 144000 | 144000 |  | None | [10 empty] | 2015-02-02 | [11 empty] | None |  |  |  | James Macintosh | 2 | 2017-03-06 09:00 | 2017-02-27 08:40 |  |  | 0¦i01x9j: | [7 empty] | 2015-01-27 |  | None |  | 2017-02-09 14:31
Project 1 | PFA-2 | Create a hand mapping tools from Project 3/NI to verify Existing mappings and map those that could not automatically map. | New Feature | Open | 1 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2016-12-07 08:20 | 2017-02-22 08:52 | 2017-02-22 08:52 |  |  |  | Outage/Outage Factors |  | 0 | 1 |  | 57600 | 0 | 136800 | 237% |  |  |  | Could use a similar tool as Constraint Hand Mapping tool |  | 100% | 100% | 136800 | 0 | 57600 |  | None | [10 empty] | 2016-12-08 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-02-24 10:59 | 2017-02-24 10:59 |  |  | 0¦i01uyn: | [7 empty] | 2016-12-07 |  | None
Project 2 | DS-32 | Use the Load Distribution from the SE files to update a Trazer Run to test the performance of that day. | Improvement | Open | 1 | Unresolved | Dev 1 | Dev 1 | Dev 1 | 2016-12-20 14:22 | 2017-02-22 08:19 | 2017-02-22 08:19 |  |  |  | Load |  | 0 | 1 |  | 144000 | 144000 |  | 0% | [5 empty] | 0% | 0% |  | 144000 | 144000 |  | None | [22 empty] | None |  |  |  | Gerry Binder |  | 2017-03-02 11:30 | 2017-02-23 11:30 |  |  | 0¦i01uzr: | [9 empty] | None
Project 5 | BACKOFFICE-37 | Add a Position Report to the FMV report. | Enhancement | Open | 1 | Unresolved | Dev 1 | Dev 1 | Dev 1 | 2017-02-16 15:43 | 2017-02-22 08:22 | 2017-02-22 08:22 | [5 empty] | 0 | 1 |  | 28800 | 28800 |  | 0% |  |  |  | Roll positions up by isoftrid |  | 0% | 0% |  | 28800 | 28800 |  | None | [22 empty] | None | [5 empty] | 2017-02-23 12:00 | 2017-02-22 10:00 |  |  | 0¦i01yv3: | [9 empty] | None
Project 4 | CLNCHR-182 | Capture Wind Forecast from PJM EdataFeed | Improvement | Open | 1 | Unresolved | Dev 4 | Dev 1 | Dev 1 | 2015-05-19 08:53 | 2017-02-22 08:40 | 2017-02-22 08:40 |  |  |  | Generator |  | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | Need to upgrade Edatafeed jar to lastest 5.2 New data seems to be available hourly at about 5 minutes past. |  | 0% | 0% |  | 57600 | 57600 |  | None | [22 empty] | None |  |  |  | Matt Tunno | 1 | 2017-02-23 08:40 | 2017-02-22 08:40 |  |  | 0¦i01wfj: | [9 empty] | None
Project 2 | DS-54 | Data Verification Tasks - Misc Tasks | Enhancement | Open | 1 | Unresolved | Dev 3 | Dev 3 | Dev 3 | 2017-02-22 08:12 | 2017-02-22 08:52 | 2017-02-22 08:52 | [5 empty] | 0 | 1 |  | 57600 | 57600 |  | 0% |  |  |  | 1. Add Constraint Historical Ability for Constraint Desc Mapper and Hand Mapper Tools 2. Add Right click menu to launch constraint in NI Panel from Constraint Desc Mapper Tool 3. Cross check Constraint Auto Mapping Jobs for specific logics certain to ISO a. ERCOT - Make sure monitor mappings are searched based on key in monitor description. Also cross check for Contingency mappings, make sure to process Line Segment/XFMR only. b. MISO - Parse the MISO constraint to look for string matchings in raw file to determine the branch name and complete the mapping. c. SPP - Update the mapping to include all the monitor lines and redesignate them to interface lines. d. PJM - Verify if the PJM Trans Facility Master file's B3 string is being used to identify the branch mappings for the Monitor line. 4. Get the accurate time frame of the right click to pass it to shift factors gen tool from Constraints Chart 5. Use calculated RT Cong prices for ERCOT while displaying Shift Factors tool instead of 0's |  | 0% | 0% |  | 57600 | 57600 |  | None | [22 empty] | None |  |  |  | Jeff Erdely |  | 2017-02-24 08:30 | 2017-02-22 08:30 |  |  | 0¦i01yvj: | [9 empty] | None
Project 1 | PFA-15 | Current UI add right click on a constraint and show shift factors, adjust these for the flow direction of the constrained line. Show prices at the highest SP time point of the constraint. | New Feature | Open | 2 | Unresolved | Dev 2 | Dev 1 | Dev 1 | 2017-01-27 11:43 | 2017-02-14 11:46 | 2017-02-14 11:46 |  |  |  | Constraints |  | 0 | 1 |  | 144000 | 144000 |  | 0% | [5 empty] | 0% | 0% |  | 144000 | 144000 |  | None | [10 empty] | 2017-02-02 | [11 empty] | None |  |  |  | Jeff Erdely |  | 2017-02-23 12:00 | 2017-02-16 11:42 |  |  | 0¦i01ylj: | [7 empty] | 2017-01-27 |  | None
Project 2 | DS-51 | Create application compare the SPP daily Temp and Permanent constraints file data. | Improvement | Open | 2 | Unresolved | Dev 3 | Dev 1 | Dev 1 | 2017-02-10 10:53 | 2017-02-22 08:58 | 2017-02-22 08:58 | [5 empty] | 0 | 1 |  | 28800 | 28800 |  | 0% |  |  |  | Indicate changes, sent changes to traders, parse information too and supply to dart system to build constraints or modify existing ones accordingly and feed that information to tranzer. |  | 0% | 0% |  | 28800 | 28800 |  | None | [22 empty] | None |  |  |  | Rick Zabrosky |  | 2017-03-20 11:00 | 2017-02-13 11:00 |  |  | 0¦i01ytb: | [9 empty] | None
Project 2 | DS-27 | Create a tool to display visually bus level detail, add ability to compare to sources at that level of detail. | Enhancement | Open | 1 | Unresolved | Dev 5 | Dev 1 | Dev 1 | 2016-12-09 11:15 |  | 2017-02-06 09:06 |  |  |  | Power Flow |  | 0 | 1 |  | 864000 | 864000 |  | 0% |  |  |  | a. Accept User Input to determine operations. i. Branch Differences 1. Also color for Characteristic changes. 2. Right click to display the changes in a table. ii. Bus Differences iii. Right Click to add new Bus/Branch/Transformer 1. On Bus add need to update associated Load/Gen Tables (4 Days) 2. Add a Load bus need to determine the load factors to be used. Need more info to determine how to handle) iv. Right click for Deletes of branches brings up panel of Constraint Information. To determine what actions to perform (Delete remap) Update MDB (4 Days) v. Right Click Delete Bus need to check Associated Tables (Load, GEN) (4 days) vi. Right click for Bus/Branch/Transformer name change, store the name change. Update the MDB 1. Store in Line_Mapping and Line_Mapping_ERCOT tables. (4 Days) vii. PJM, try mapping name changes using Branch Mapping/B1B2B3 files of the |  | 0% | 0% |  | 864000 | 864000 |  | None | [22 empty] | None |  |  |  | Gerry Binder |  | 2017-03-15 11:30 | 2017-02-01 11:30 |  |  | 0¦i01uy7: | [9 empty] | None
Generated at Wed Feb 22 09:04:58 EST 2017 by Dev 1 using JIRA 6.3.6a#6336-sha1:a9dd8c0eed071956feea63e7f8b086dfe58acb6e.